## home page
header dropdown icon aligment | completed
header hamburger bg overlay | completed
header hamburger dropdown icon | completed
header - notification button
header - responsive mobile
hero banner- laptop view not correct and (height, title, button disalign) | completed
Find what you need - slider box left -right visibility not as design | pending | Need Extra Time to resolve the issue(Autoplay Isuue)
Find what you need - not as lap view |  | Its Same as in the design
about - counter initail onload counter showing value | completed
Our Team - slider box social media icon hover missing | completed
Our Team - slider size is big |  | Need Extra Time to resolve the issue
Our Team - text width not correct | completed
Blog & Article - lap view | completed
Blog & Article - slider box hover arrow size bigger in lap | completed
Blog & Article - slider box hover arrow overlap text | completed
form section- min-height to fix tab change height issue
form section- host a workshop form datepicker height, placeholder | completed
Follow us on Instagram - slider on drag issue- (left right side gap) | pending
footer- intersmat logo size bigger lap | completed
footer- menu title policies change to quick links | completed
footer- social media icons size bigger compared to design - lap | completed
Console error
Form > Phone number > Placeholder missing | completed
Social media > Place the "share links where we can explore your work "in the text area | Clarification | Need Clarification
Blog & Article > Missing padding on screen reduce | completed | https://jam.dev/c/fdc37923-e956-4ffb-b182-e1ace86afc73
Footer/Contact/Blog detail > Social media icons> Maintain the style on hover | completed
Drop-down menu > There is a difference b/w the desktop and mobile |  | The content inside is used as dummy text and can be customized.
Header > Cart > Difference style over the pages |  | https://jam.dev/c/5ad29afb-d3a0-4f43-9fb5-ca75cdec096b
Header > Cart > Cart icon is not visible on mobile view
Chatbot icon > It would be better to show only the cms pages

## blog article detail
Blog listing - hero banner- black overlay color change(light color in design) - common in all inner pages | completed
Blog listing - video missing- blog box - src issue | completed
Blog detail - listing style missing | completed
Broken Image | completed
Back to Blogs > link > change Under-line color to black on hover | completed

## team
team box - social media icon hover missing | completed
title description text weight and width not as design | completed

## contact
form section- host a workshop form datepicker click issue- not working properly | completed
follow us- icons size bigger compared to design | completed
form - submit button change to a tag to button | completed
form- Field height issue date and yoga | completed
call to action not working | completed
Form > Phone number > Placeholder missing | completed
Social media icons > Font color difference on hover | completed | https://jam.dev/c/d37b1054-cfb3-487b-8d58-6e6b83d1b161
Contact > Phone number and email > Tel tag and mail to " missing | completed | https://jam.dev/c/5d01916b-bce5-4f4b-a533-a6c0193ad03e
Common > All forms >Drop-down > BG Text shows behind the drop-down menu container > Mobile view | completed | https://jam.dev/c/326c8d11-92ce-4adb-894e-2e6d67c500cd
Social media icons > Text visibility issue on hover (mobile view) | completed

## testimoials
testimonial box image hover missing | completed
design not matching in lap | completed
sections gap size bigger | completed
testimonial box quote image color change | completed
Load More icon missing | completed
Double quotes > icon color change | completed | https://jam.dev/c/f6108206-32c4-42f3-9fc9-138bd5c729ab

## schedule
button breaks in lap | completed
Schedule > Date picker > Current date is not highlighted
Mobile view > Both tabs are highlighted when clicking on the "view more"

## legal pages
privacy policy - section gap- top gap smaller and bottom bigger- not matching with design | completed
font size difference | completed
list style tick mark missing | completed
check laptop layout | completed
refund - section gap issue | completed
cookie- section gap issue | completed
Mobile > Bullet points missing | completed
Need space b/w the content and the title , it looks so conjested | completed

## Membership Packages
section gap deffernece in lap | completed
button icons are missing (src issue) | completed
Price > Value should be in the bold style | completed
Mobile > Sie menu > Drop-down > BG Text shows behind the drop-down menu container | completed
Add hover effect on button | completed
Side menu bar > Seperation lines are missing in the mobile view
Side menu bar > Bullet points are missing in the mobile view
Header > Drop-down menu overlaps with the text

## cart
remove button alignment issue | completed
change button hover color to red will be better | completed
Place the delete button under the dotted tab additionally it would be better to show only the icon and remove the text | completed
Reduce the image size on the mobile:Refer Udemy | completed

## workshop-listingdetail
listing - hero-banner - image change | completed
listing - section gap chnage in lap
detail - banner image change
detail- section gap in lap

## checkout
form - Remove default label from select country dropdown (choose country) | in progress | ajay
form - phone field country select dropdown issue (overflow hidden)
Phone number > Placeholder missing
Reduce the image size on the mobile:Refer Udemy
Country or phoner number drop-down > Remove the page scroll on mobile view

## about
Our Approach - animation smoothness problem | in progress
load more button icon missing

## auth pages
verify OTP- submit button hover missing | completed
form- text not visible when autofill > Reg and log in | completed
change submit a tag to button | completed
agree button terms & privacy policy link not working | completed
login here and signup here button not working - need to navigate onclick | completed
Email field > Placeholder missing | completed | Not in the design
Input text should be active color > Log in and Reg form | completed
Reg form > Star icon missing in the Create password field | completed
Phone number > Placeholder missing | completed
Verify your email > Input text should be active color | completed
All buttons and links should be linked | completed

## hatha-yoga
faq - accordion buttons collapse icon alignment | completed
Related Sessions - Slider right-side portion missing | pending | It is Same as Home page Slder need time to fix
hover transition not smooth | completed
gallery load more button icon missing | pending | Load more icon is not in the design

## wellness-sessions
Yoga Programs - slider box transitions not smooth | completed

## pre-recorded-class
design not correct..need to check overall page | pending | Page In Progress

## dashboard
pending